## Project Planner
Food Nutrition Breakdown App
[5 empty] | Period Highlight | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 Collect Data | 1 | 1 | 1 | 1 | 100%
1.2 Create Project Plan | 1 | 3 | 1 | 3 | 100%
1.3 Create WBS and schedule | 1 | 1 | 1 | 1 | 100%
1.4 Conduct user research | 1 | 1 | 1 | 1 | 100%
1.5 Create Software Design Document | 3 | 4 | 3 | 4 | 100%
1.6 Map User Flow | 3 | 1 | 3 | 2 | 100%
1.7 Design Screen Wireframes | 4 | 2 | 4 | 2 | 100%
1.8 Validate Wireframes | 5 | 1 | 5 | 1 | 100%
2.1 Develop User Interface | 6 | 3 |  |  | 0%
2.2 Develop Screen Interconnectivity | 9 | 3 |  |  | 0%
2.3 Implement Provided Database | 9 | 2 |  |  | 0%
2.4 Implement Food Search Feature | 12 | 2 |  |  | 0%
2.5 Implement Nutrition Breakdown Feature | 14 | 4 |  |  | 0%
2.6 Implement Nutrition Range Feature | 18 | 3 |  |  | 0%
2.7 Implement Nutrition Level Filter | 21 | 2 |  |  | 0%
2.8 Implement Dietary Level Filter | 21 | 3 |  |  | 0%
3.1 Unit Testing | 24 | 1 |  |  | 0%
3.2 Alpha Testing | 25 | 1 |  |  | 0%
3.3 Acceptance Testing | 26 | 1 |  |  | 0%
4.1 Fix Bugs | 27 | 3 |  |  | 0%
4.2 Gather Feedback | 27 | 2 |  |  | 0%
4.3 Enhance Features | 30 | 3 |  |  | 0%
4.4 Sanity Test | 33 | 2 |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%